CALENDAR

TPS & Publishing Romania

**INFORMATION FOR FOREIGN PUBLISHING HOUSES:**

|  |  |  |
| --- | --- | --- |
| 30-31 January 2023 | An internal CENNAC committee is being established for the 2023 TPS & Publishing Romania call for applications | 2 days |
| 1 February 2023 | The launch of the 2023 TPS & Publishing Romania’s call for applications | 1 day |
| 1 February-8 March 2023 | The submission, by foreign publishers, of the application files, according to the Guidelines of the two financing programmes. This call for applications strictly concerns titles to be published in 2023. | 5 weeks |
| 8 March 2023 | The final day of the call for applications | 1 day |
| 9-10 March 2023 | The applications received are being verified by the internal CENNAC committee | 2 days |
| 13 March 2023 | The candidates are being contacted if their applications are not complete | 1 day |
| 14-15 March 2023 | The candidates can supply the missing files to their applications | 2 days |
| 16 March 2023 | The final assessment of the documents received from the candidates | 1 day |
| 17 March 2023 | The final list of the eligible applications | 1 day |
| 20-31 March 2023 | The assessment, by a panel of independent experts, of the eligible applications | 2 weeks |
| 3-7 April 2023 | The validation of the panel’s evaluation, by the Board of Directors of the Romanian Cultural Institute | 1 week |
| 10 April 2023 | The publicizing of the list of evaluated editorial projects, upon prior validation by the Board of Directors of the Romanian Cultural Institute, on the platforms [www.cennac.ro](http://www.cennac.ro) and [www.icr.ro](http://www.icr.ro) | 1 day |
| 11 April-31 May 2023 | The conclusion of the grant contracts with the winning publishing houses, with 2023 as term for the reimbursement by the Romanian Cultural Institute | 7 weeks |

**OPEN CALL FOR INDEPENDENT EXPERTS:**

|  |  |  |
| --- | --- | --- |
| 6 February 2023 | The launch of the open call for independent experts, to be part of the evaluation panel of TPS & Publishing Romania 2023 | 1 day |
| 7-19 February 2023 | The submission of the application files | 2 weeks |
| 20-26 February 2023 | The publication of the list of eligible applications | 1 week |
| 27 February-5 March 2023 | The election of the independent experts to be part of the evaluation panel, by the Board of Directors of the Romanian Cultural Institute | 1 week |