**Calendarul sesiunii de selecţie program Cantemir 2025**

|  |  |  |
| --- | --- | --- |
| **Termen** | **Perioadă** | **Activitate** |
| 1 **day** | February 17 | Launch and publication of the project selection criteria on the ICR website for the CANTEMIR 2025 Program |
| 31 calendar days | February 17 – March 19, **4:00 PM** | Project submission |
| 19 calendar days | February 17 – March 7, **3:00 PM** | Submission of applications for independent evaluators |
| 8 working days | March 10 – March 19 | Selection of independent evaluators |
| 12 working days  | March 20 – April 4 | Stage I of selection: Administrative eligibility check of applications |
| 1 working day | April 7 | Publication of the list of cultural proposals admitted after Stage I of the selection session |
| 3 working days | April 8 – April 10, **4:00 PM** | Appeals submission |
| 3 working days | April 11 – April 15 | Appeals settlement for the 1st stage of selection session |
| 1 working day  | April 16 | Publication of the results of the administrative eligibility check of applications |
| 17 working days  | April 17 – May 15 | Implementing the 2nd stage of the selection session: projects evaluation |
| 1 working day  | May 16 | Publication of the results of Stage II of the selection |
| **3 working days**  | May 19 – May 21, **4:00 PM** | Appeals submission |
| **3 working days**  | May 22– May 26 | Appeals settlement for the 2nd stage of selection session |
| 1 working day | May 27 | Displaying the results of selection session for the *Cantemir* Programme 2025 |
| 17 working days | May 28 – June 20 | Signing the financing contracts |